## Backlog
Backlog | Story Point Estimate | Priority
As someone donating, I want to be able to find the nearest recycling location | 10 | 2
As customer at a coffee shop I want to be able to redeem my discounts | 5 | 1
As environmentally aware person I want to be able to invite people to the app | 4 | 2
As somone donating, I want to input my points quick and easy | 3 | 1
As a customer I want to be able to see how many points we have available | 3 | 2

## Sprint1
Story | Backlog | Estimate(hours) | Who | In Progress | Done
As a developer, I want to create the foundation for the dashboard, the code input, and the user profile. | Structure Discussion and Planning | 1 | Everyone
| Aesthetic Design and Unification | 1 | Everyone
| Daily Scrums | 15min x 5 | Everyone
| Create dashboard html | 1 | Kibum Park
| Create dashboard css | 1 | Kibum Park
| Create Navigation Bar | 30 min | Kibum Park
| Synchronize Nav Bar | 30 min | Everyone
| Create input html | 1 | Charles Huang
| Create input css | 1 | Charles Huang
| Create account html | 1 | Aleksandra Sorokina
| Create account css | 1 | Aleksandra Sorokina
| Assembly | 1 | Everyone
| Debugging Session | 1 | Everyone
| Final Review Session | 1 | Everyone
Screen Size: 1440 x 900
Font: Organic Fruit
Top Bar Height: 70px

## Sprint 2
Story | Backlog | Estimate(hours) | Who | In Progress | Done
As environmentally aware person I want to be able to invite people to the app | Connect Pages to Database | 1 | Sasha
| Testing Database | 1 | Sasha
| Hiding API Key | 1 | Sasha
| Finding Fonts | 1 | Charles
| Create Barcode HTML | 1 | Charles
| Create Barcode CSS | 1 | Charles
Planning | Create Location Finder Page HTML | 1 | Kibum
| Create Location Finder Page CSS | 1 | Kibum
| Connect Pages Together via Links | 1 | Kibum
| Database Instructional Session | 1.5 x 3 | Everyone
| Assembly | 1 | Everyone
| Debugging Session | 1 | Everyone
| Final Review Session | 1 | Everyone
16.5

## Sprint 3
Story | Backlog | Estimate(hours) | Who | In Progress | Done
As someone donating, I want to be able to find the nearest recycling location | Create User Database | 1
Add three users data: -Picture -Name -Points -Join Date
Each user should be each member for indiviudal testing
| Create Input Database | 1
Planning | Add input data for three codes: -Code Name -Code Points
| Add in an input text field for the Input Code Page | 1
Replace Code Div with a working textfield.
| Connect that textfield to databases functionality. | 0.5
| Write HTML: -Input the code -Compare the code to the input database -If it's valid, modify the "Point" data for the User database. -Give confirmation message at the input page. | 1
| Color Coordinate All the Pages Unify CSS Into a central theme | 1
| Develop Each Member's Own Github Branch | 0.5

## Sprint 4
Story | Backlog | Estimate(hours) | Who | In Progress | Done
As customer at a coffee shop I want to be able to redeem my discounts | Create rewards html | 1
| Create barcode html | 1
| Create rewards css | 2
| Create barcode css | 2
Planning |  | 1
Final Overview |  | 4